## Slide 1
EXPloring blablacar market opportunities in india
1
Company Restricted © Capgemini Invent 2023. All rights reserved |
1
BlaBlaCar market research proposal | September 2023

## Slide 2
Our understanding of your needs
Our approach
Our assets to support you
Appendix
1
2
3
4
BlaBlaCar market research proposal | September 2023

## Slide 3
Our understanding of your needs
Our approach
Our assets to support you
Appendix
1
2
3
4
BlaBlaCar market research proposal | September 2023

## Slide 4: BlaBlaCar has seen good traction on its Indian platform, despite having stopped investments in 2017
  BBC opens carpooling platform in India
2015
  Launch of local features (e.g. Woman-only ride shares)
  3M seats have been offered on the site
2016
  BBC closes its Indian office and stops Indian-only investments
  Platform remains open
2017
  4 million active users
  Almost x2 growth yoy with no direct investment
2022
  ~600k rides per month
  BBC is thinking about:
    Relaunching carpool investments
    Launching Pro marketplace
2023
…
Sources: Business today, ET Auto

## Slide 5: Specific government and user concerns about carpooling in india have directly impacted ride sharing players
The MV Act restricts vehicles being used for hire without permits
However, the debate arises when distinguishing profit-driven carpooling from cost-sharing models; the legality of such distinctions hasn't been conclusively tested
Carpooling remains in a grey area of central and regional regulations
Safety and reliability are major concerns for riders in India
Ride sharing apps are putting in place strong safety features to prevent scams and ensure riders security (incl. women only rides)
Ride cancellation by drivers is riders’ top issue with taxi apps in India (47%), followed with surge pricing (32%), with little impact from the regulation
Sources: LocalCircles 2022 survey on App taxi usage in India, Economic Times, Entrackr, zeebiz

## Slide 6: BlaBlaCar is looking for some support to assess the Indian mobility market before reinvesting in its carpooling platform and launching the Pro marketplace
Phase 1 – Provide an overview of the Indian shared mobility landscape and assess the market opportunity for the Pro marketplace
Shared mobility market overview through secondary research
Deep dive on the bus market and overview of its supply chain and commercial structure through desk research and industry players’ interviews
Phase 2 – Define BlaBlaCar’s carpooling and Pro Marketplace market fit in India
Addressable market and target user definition
Gap analysis between BlaBlaCar existing products and customer expectations through competitors’ benchmark and customer interviews
Updated concepts acceptability

## Slide 7
Our understanding of your needs
Our approach
Our assets to support you
Appendix
1
2
3
4
BlaBlaCar market research proposal | September 2023

## Slide 8: Market overview proposed approach
Goals
Main activities
Methodology
Deliverables
Provide an overview of the Indian shared mobility market
Deep dive on the bus industry and assess the market opportunity for the Pro Marketplace
In select hubs, analyze the shared mobility landscape across main alternatives: personal car, bus, train and plane
  Market size and evolution for each alternative
  Pricing range and intercity network for each alternative
  Top players overview
  For carpooling: Overview of central and state regulation
In select hubs, deep dive on the private organized bus market
  Market size of the private bus network and its evolution
  Online vs offline booking trends and evolution from 2018-2028
  Top bus operators overview with network, size, pricing, supply type
  Top bus supply chain players overview (focus on IMS and GDS)
For a limited sample of N=10 across select Private Bus Operators, Solution Providers and OTAs to be interviewed, analyze the IMS/ GDS in place and commercial terms being used
  Overview of the IMS and GDS used and rationale
  IMS and bus operators’ perception towards BBC Commercial terms overview
Shared mobility market overview
Deep dive on the bus market with supply chain vendors and commercial terms overview
Executive memo highlighting key learnings
Desk research based on publicly available sources, premium databases, operators’ websites and BlaBlaCar own data and analysis
N=10 Interviews (face-to-face and online) conducted across OTAs / Private Bus Operators/ Solution providers with marketing, sales/ distribution/ vendor/ customer/ business teams
Phase 1
Phase 2

## Slide 9: Market overview Detailed project plan
Activities | Activities | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
Capgemini Invent / BlaBlaCar sync | Capgemini Invent / BlaBlaCar sync |  |  |  |  | 
1.A | Shared mobility landscape overview – Desk research |  |  |  |  | 
1.A.1 | Mobility landscape (personal car/bus/train/plane) analysis in 7 identified cities – Network within intercity limits primarily Tier 1 cities |  |  |  |  | 
1.A.2 | Central and State Carpool regulations overview |  |  |  |  | 
1.A.3 | Deep dive on bus industry in target cities of India |  |  |  |  | 
1.B | Bus market structure: Tech vendors / Commercial terms overview – Primary Interviews (N=10: OTAs/ Solution Providers/ Bus operators ) |  |  |  |  | 
1.B.1 | BlaBlaCar stakeholder interviews |  |  |  |  | 
1.B.2 | Finalization of Discussion Guide |  |  |  |  | 
1.B.3 | Recruitment and Interview of experts |  |  |  |  | 
1.B.4 | Content analysis |  |  |  |  | 
1.C | Deliverables finalization & key learnings summary |  |  |  |  | 
Interim workshops/sync
Kick off
Final review
Phase 1
Phase 2
Notes: Analysis of 7 cities + roads + competitors (some information about the competitive benchmark)
Deep dive bus industry from week 2
Multiple meetings to get tech / commercial details

## Slide 10: Market overview research methodology
2. SECONDARY RESEARCH
Deep-dive in the Mobility market and Bus industry in Tier1 cities in India; Overview of intercity mobility market with focus on 2-3 identified hubs* with carpooling regulations
3. CG DOMAIN EXPERTS
Obtain market understanding of value chain of mobility marketplace solution for buses along with identification of key players primarily for IMS and GDS
4. PRIMARY RESEARCH – Bus Operators, Solution Providers & Competitors
Qualitative Research: Framing of questions and probing is critical to elicit response. Direct questioning might not work, specifically when asking for sensitive information.
Discussion guide is used to steer the discussion, while a content analysis is done to infer from the recorded interviews
1. KICK OFF WITH BLABLACAR
Finalise regions/cities and product(s) in scope, deep-diving further into background & context of business problem. Understand the information already in place with BlaBlaCar regarding markets, competition and customers
6. ITERATIVE COLLABORATION
Regular cadence calls with BlaBlaCar stakeholders to provide project updates - at specified milestones is highly recommended to minimise Expectations vs Deliverables deltas
5. DATA TRIANGULATION and RECOMMENDATIONS
Integration of data and analysis from secondary and primary sources is done to build linkages and generate comprehensive insights.
Recommendations for preferred hub/route
We believe there is an efficiency in utilising a hybrid approach using secondary sources and primary research to generate the desired analysis – each data source has its pros and cons. But taken together, it enhances the quality of insights
*Hubs are the cities from where majority of bus routes to different cities/destinations originate. The hubs (Delhi, Mumbai/Pune and Bengaluru/Hyderabad etc.) will be finalized in consultation with BlaBlaCar stakeholders and are part of 7 cities to be analyzed.
We believe the most efficient way to conduct the research would be to combine a variety of research methodologies and have a collaborative approach with client
Phase 1
Phase 2

## Slide 11: To assess BBC product fit in india, we recommend a three-step approach
Addressable market, target users and preferences assessment
User mindsets, challenges and needs understanding
Final concept validation
Expected outcomes
Phase 1
Phase 2
Goal
Addressable market sizing
Transportation habits and preferences
Awareness of carpooling and bus platforms including BBC
Understand market potential and preferences for carpooling and bus for inter-city travels
Understand general attitudes towards carpooling, their needs and mobility challenges
Identify gaps in BlaBlaCar as well as competitor’s products and brand perception of BlaBlaCar
Deep dive into user mindsets, challenges and needs while using the platform
Evaluative scores on overall likeability, uniqueness, relevance, credibility, comprehension, intention to use
Diagnostics on likes, dislikes, reasons for wanting to use
Validate finalized concepts based on audience acceptance of key parameters
1
2
3
Out of scope

## Slide 12: Addressable market, target users and preferences assessment
Purpose and scope
Methodology
Outcomes
Contingencies
For the total population being considered, evaluate the total addressable market for carpooling and bus services
Identify the key target users for different modes of transportation especially carpooling and bus services
Understand the habits and practices for inter-city travel and the main drivers by transportation mode and platform type (online, offline)
Research questions
  Travel habits including inter-city travel (incl. frequency, modes)
  Booking channels used
  If booked online, list of sites aware of (e.g., BBC etc.) used and rationale
  Study design
  Face-to-face quantitative study to be conducted
  A structured quantitative questionnaire to be used
  Random Listing study to evaluate incidence of usage followed by the main study to understand usage/ practices among users/ / non-users of platforms
  Audience (to be fine-tuned based on outcomes of phase 1 and platform data analysis)
    2000 participants (400 per city)
    SEC A, B, C respondents
    Males and females
    Staying in one of the locations: Hyderabad, Bengaluru, Mumbai, Delhi, Pune
    Inter-city travelers (> 50 kms from city )
    5 to 6 hours max of travel time and/ or overnight journey
Learnings from Phase 1 (Market Understanding), through Desk Research, inputs received from client stakeholders
Target audiences/ age group/ SEC, locations to be finalized in consultation with the client​
Questionnaire to be designed by the CG research team and finalized in consultation with the client​
Key target users for carpooling and bus services
Current carpooling and bus services being used
Drivers for using / not using carpooling and bus services
Improvement areas for carpooling and bus services
Phase 1
Phase 2
1

## Slide 13: Deep dive into user mindsets, challenges and needs
Purpose and scope
Methodology
Outcomes
Contingencies
Understand general attitudes towards carpooling and bus ride booking, their needs and mobility challenges
Identify gaps in BlaBlaCar as well as competitor’s products and brand perception of BlaBlaCar
Understand societal, macroeconomic (payments, etc.), regulatory, and mobility trends impacting users
Research type
  Observational research or shadowing with open ended questions to understand their lifestyles, surroundings while capturing mindsets
  Questionnaire will be around perception of carpooling, travel patterns, usage patterns, booking challenges, payment trends, etc.
  Study design
  Research in user’s environment in tier 1 cities
  A structured qualitative questionnaire to be used
  Audience
    About 30 participants (mix of riders and drivers) in Bangalore, Delhi, Mumbai, Pune, Kolkata or Chennai
    Users who are new and/or have used carpooling services or bus booking platforms (BlaBlaCar or competitors)
    Users who have rented car using booking platforms
Hypothesis based on existing market study (if any)
Consumer profiles – carpooling drivers, carpooling riders, bus riders
Learnings from Desk Research, inputs received from client stakeholders
Target audiences/ age group/ SEC, locations to be finalized in consultation with the client​
Define personas or behavioural archetypes to help BlaBla car target potential consumers and address gaps for existing consumers
Identify opportunity areas where BlaBla car can thrive in the Indian market
Phase 1
Phase 2
2

## Slide 14: Out of scope - Final concept validation
Purpose and scope
Methodology
Outcomes
Contingencies
Assessment/ Evaluation of BlaBlaCar’s finalized concepts for the following:
  Carpooling platform
  Pro Marketplace
  To understand the fit of the concepts in India among potential user
Concept formulation and questionnaire design
  Initial Concepts to be provided by the client (what is being proposed)
  To follow format of need state, benefit statement, support statement, payoff
  Design questionnaire for both concepts with complete information covering first thoughts, spontaneous likes/ dislikes, attribute ratings, intention to use
  Study design
  Face-to-face quantitative study to be conducted
  A structured quantitative questionnaire to be used
  Finalized concepts would be exposed to the respondent
  Audience (to be fine-tuned based on outcomes of phase 1 and data analysis)
    700 participants (350 carpooling users / 350 bus platform users)
    SEC A, B and C respondents
    Males and females
    Staying in one of the locations: Hyderabad, Bengaluru, Mumbai, Delhi, Pune
    Inter-city travelers (> 50 kms from city )
    5 to 6 hours of travel time max and/ or overnight journey
Learnings from Phase 1 (Market Understanding), through Desk Research, inputs received from client stakeholders
Target audiences/ age group/ SEC, locations to be finalized in consultation with the client​
Need the final concepts for carpooling and pro marketplace required for testing quantitatively
Questionnaire to be designed by the CG research team and finalized in consultation with the client​
  Awareness, usage and perceptions of booking apps
  Spontaneous likes, spontaneous dislikes of concepts
  Importance and Ratings of the concepts
  Scores on appeal, uniqueness, relevance, believability and comprehension of the concepts
  Intention to try/ improvement areas
Phase 1
Phase 2
3

## Slide 15: Product Fit detailed project plan
N. | Activities | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11
2.0 | Competition benchmark |  |  |  |  |  |  |  |  |  |  | 
2.1 | Addressable market, target users and preferences assessment |  |  |  |  |  |  |  |  |  |  | 
2.1.1 | Study set up (audience targeting, questionnaire and field brief) |  |  |  |  |  |  |  |  |  |  | 
2.1.2 | Face-to-face quantitative interviews |  |  |  |  |  |  |  |  |  |  | 
2.1.4 | Survey insights and conclusions (extent of product fit/ gaps if any) |  |  |  |  |  |  |  |  |  |  | 
2.2 | Deep dive into user mindsets, challenges and needs |  |  |  |  |  |  |  |  |  |  | 
2.2.1 | Study set up (audience targeting, questionnaire and concepts) |  |  |  |  |  |  |  |  |  |  | 
2.2.2 | Face-to-face qualitative interviews |  |  |  |  |  |  |  |  |  |  | 
2.2.3 | Survey insights and conclusions |  |  |  |  |  |  |  |  |  |  | 
2.3 | Final concepts validation |  |  |  |  |  |  |  |  |  |  | 
2.3.1 | Concept creation |  |  |  |  |  |  |  |  |  |  | 
2.3.2 | Study set up |  |  |  |  |  |  |  |  |  |  | 
2.2.3 | Face-to-face quantitative interviews |  |  |  |  |  |  |  |  |  |  | 
2.3.4 | Survey insights and conclusions |  |  |  |  |  |  |  |  |  |  | 
Phase 1
Phase 2
Out of scope
Notes: High level benchmark
Gap analysis in primary reasearch

## Slide 16: Collaborative Governance Model
Steering
committee
Core Team
Steering committee
Be responsible for the resolution of escalated issues
Monitor status (scope, schedule, budget) of the project
Review and approve project scope, deliverables, change request and budget
Subject Matter Experts
SMEs with deep knowledge of the mobility market solutions
Core Project Team
Ensure program objectives are met within timing and scope
Ensure project tasks are being performed according to plan
Escalate risks and issues early and often through remediation
BlaBlaCar
Capgemini
Resource Key
Project manager
Primary research team
User research team
CADENCE
Core Team - Connects with BlaBlaCar team per timeline* proposed:
  Review project progress/increments at micro-level and agree on next action item set
  Course correction (if and as required)
  Mitigate challenges (if and as required)
Steering committee – bi-weekly connect/workshop or as deemed fit to:
  Review project progress and interim reports
  Review project risks/challenges etc
  Strategic decisions, if any
Single point-of-contact for feedback/escalations
BlaBlaCar
Program Sponsor
Project lead
Single point-of-contact for delivery
Secondary research team
Industry SME

## Slide 17: Assumptions for Estimating Efforts, Timelines and Successful Engagement
Stakeholder connect and bandwidth
  The engagement will be collaborative with BlaBlaCar’s stakeholders engaged to work with Capgemini team
  Required stakeholders from BlaBlaCar will be available for meetings/workshops to provide inputs/validate deliverables. Any delays due to unavailability of stakeholders or documentation required, may have an impact on the project effort and timeline
Pricing and Timelines
  The pricing and timelines of the study are determined with the assumption of analyzing a maximum of 7 Indian cities via secondary research and 5 cities via primary research
  The pricing estimates are limited to efforts and methodology outlined in this document
  Any additions in scope, timelines will require separate feasibility and efforts
  Market Analysis Assumptions
  A maximum of 7 cities (primarily Tier 1) in India will be analysed from secondary research perspective. The cities analyzed will be the departure point of the route
  For the analysis, the cities with road distance of more than 50 kms and a maximum of 5 to 6 hours of travel time and / or overnight journey will be considered as intercity
  For performing analysis on different tech layers along the value chain, BlaBlaCar will share the details of its platform(s). Interpretation of technical architecture of a platform is out of scope
  Carpooling within city limits (home to office / office to home) is out of scope
  Carpooling regulations at central and state (of target cities) level will be analysed. Legal interpretation of regulations is out of scope
Assumptions & Limitations (1/2)

## Slide 18: Assumptions for Estimating Efforts, Timelines and Successful Engagement
Primary Interview Assumptions
  A limited sample of N=10 OTAs, Solution Providers and Bus Operators would be interviewed
  Information will be collected on a best effort basis given the restricted timeline
  The relevant International codes of conduct for market research and data privacy regulations would be adhered
  Personal information about the experts being interviewed would not be shared
  The exact split of the sample size would depend upon availability of the expert / nature of information being sought
  Any information which is seen as sensitive or confidential in nature may not be shared by the expert
  The focus would be to gather information would be collected at the overall level, rather than at company level
Assumptions & Limitations (2/2)

## Slide 19
Our understanding of your needs
Our approach
Our assets to support you
Appendix
1
2
3
4
BlaBlaCar market research proposal | September 2023

## Slide 20: We have major assets to support you in this project
A strong and lasting presence on the Indian market
An India-based research center of excellence along with design/CX expertise through frog
A proven expertise in the mobility sector internationally
The ability to leverage subject matter experts across the projects core components (engineering, product, design)
01
02
03
04

## Slide 21: A strong and lasting presence on the Indian market
MUMBAI
432
HYDERABAD
436
PUNE 446
BENGALURU
587
CHENNAI
121
NCR
1113
KOLKATA
51
Capgemini Invent India has over 3200 consultants working across 7 major hubs
Invent has honed its reputation as a leading management consultancy by combining strategy, technology, data science, creative design, and engineering expertise with an inventive mindset
Our strategy consulting is collaborative, partnering with our clients to innovate and transform their business, enabling them to navigate today, while plotting a course for the future.
Our frog design studios are leaders in the design industry

## Slide 22: We have access to a range of premium databases to provide strategic insights
REPRESENTATIVE SETS
INTERNAL INTELLIGENCE
SMEs from Automotive domain and technological aspects of a digital solution with deep expertise in Indian market
INTERVIEWS & SURVEYS
PUBLICLY PUBLISHED
STUDIES
IN-HOUSE
INTERVIEWS & SURVEYS
with a network of experts as well as a panel of new / existing consumers through phone calls/ online techniques to gain powerful insights
PUBLIC SOURCES
Publicly available information related to regional stats, economy, key trends etc.
Capgemini accelerators work in background to analysis and synthetase in very short time.
In-house SME insights
Insights from
Capgemini reports
In-house Panel Procurement Team for vendor selection, administrative support and coordination
Offering local language support for interviews/ moderation, questionnaire/ discussion guide translations
Strong data expertise to provide multi-mode sampling, de-duplication, and data checks to ensure data quality
Pool of hard-to-reach, high-quality, online & offline, B2B, B2C, ITDM, and healthcare census samples
Access to over 70 million panelists across 80+ countries from our 150 certified global sample partners
PANEL - GLOBAL OUTREACH

## Slide 23: WE BRING A PROVEN TRACK RECORD HELPING CLIENTS WORLDWIDE in the mobility sector (1/5)
CREATION OF A FREE-FLOATING CAR-SHARING SERVICE IN EUROPE
CONTEXT
SOLUTION
IMPACT
The client was considering entering the car sharing market in Spain, more specifically in the city of Madrid
The client required solid market research to understand the existing potential and analyze when to launch their new business model
PESTEL Analysis: Analysis of macro-factors that allow the identification of externalities that affect the implementation of the service
User profile: allows to identify demand drivers and local specificities in terms of users
Competitive positioning: Analysis of the main competitive factors that allow adjusting the service offer to each market, analysis of competitors and best practices
Service Area Analysis: Strategic evaluation of the car-sharing service coverage areas
Demand Analysis: Dimensioning of the current market and its projection for 5 years
Fleet sizing: Strategic fleet sizing for service launching
Service go/no-go evaluation
Market study carried out and demand projection
Optimal fleet and suggested area of service coverage
Strategic positioning
Launch of the car-sharing service in Madrid and a few years later also in the city of Paris

## Slide 24: WE BRING A PROVEN TRACK RECORD HELPING CLIENTS WORLDWIDE in the mobility sector (2/5)
SCALING-UP STRATEGY AND BUSINESS PLAN FOR A CAR SHARING START-UP IN INDIA
CONTEXT
SOLUTION
IMPACT
The company is the second entrant in the car sharing start-up market in India
The company had completed its MVP in few locations in North India and wanted to expand its operations in other parts of India
For the same, the company was raising funds and looking for investment partners to help them scale up the business
Engaged with the founder/ top leadership team to understand the business model and future plans
Defined the potential business models (CVP) and how the start-up would transition from an asset-heavy to an asset-light business model
Worked closely with the leadership team to define the GTM strategy in different states/ cities and the supporting Marketing programs
Developed the investment estimates and pro-forma financials for the following 3-year horizon
Developed the investment thesis for presentation to the potential investors
Defined the detailed business plan along with the key assumptions and implications on the underlying operating model and operating parameters/ KPIs
Clearly defined product portfolio as well as the target customer segments and the supporting marketing/ customer acquisition plans
Created the pitch deck for potential investors along with the investment thesis

## Slide 25: WE BRING A PROVEN TRACK RECORD HELPING CLIENTS WORLDWIDE in the mobility sector (3/5)
ONLINE MARKETPLACE FOR AN INDIA CV OEM’s AFTERSALES SERVICE
CONTEXT
SOLUTION
IMPACT
Client’s fleet owners already had their informal networks of garages/ mechanics to service their fleets. But, maintenance of vehicles, was still a bigger business problem, involving scheduling issues, timing issues, pricing issues and quality issues
In order to synthesize this market and bring all stakeholders on a common digital platform the client required different mobile applications
We created a marketplace with hybrid mobile apps for fleet manager, driver and mechanic to digitize order request from creation to billing
Built the mobile apps including CMS, user management and geo location services
For pilot phase of 3 months, apps were rolled out in 3 languages English, Hindi and Tamil and target customers being fleet managers, drivers and mechanics operating on Mumbai-Delhi, Chennai – Bengaluru and Chennai-Kolkata routes
24*7 service available to cater to vehicle breakdown/servicing requests extending to Tier 3 and 4 cities as well
Quick turnaround time to complete vehicle service request within stringent SLAs

## Slide 26: WE BRING A PROVEN TRACK RECORD HELPING CLIENTS WORLDWIDE in the mobility sector (4/5)
DIGITAL VEHICLE PASSPORT (PROOF OF VALUE) FOR GERMAN PV OEM IN INDIA
CONTEXT
SOLUTION
IMPACT
Client has an incubation center, where they test, validate and support various innovative ideas and solutions, as part of their intra-entrepreneurial initiative
Digital vehicle Passport is one of such initiative, from the incubation center where client wanted to test the Solution’s Proof of Value for a specific country
Proof of Value is intended to support and strengthen decision making for building the solution involving time and resources
Built uses cases of the solution and created a framework to test Digital Vehicle Passport Proof of Value on Customer Desirability, Technical Feasibility & Business Viability
Created entire DVP Business model in Lean Canvas and validated solution hypothesis for its uses case for Customer, Business and Technology.
Conducted qualitative research and focus industry professional research to test DVP understanding and market fit.
Shortlisted technologies suitable for DVP Solution, identified criteria's for evaluation framework and recommended best suited technology for DVP Solution
Provided complete Business Case for DVP
Project is Ongoing

## Slide 27: WE BRING A PROVEN TRACK RECORD HELPING CLIENTS WORLDWIDE in the mobility sector (5/5)
STUDY OF CONSUMER BEHAVIOR IN EV MARKET IN INDIA
CONTEXT
SOLUTION
IMPACT
Provide consumer insights for the thought leadership paper prepared by the Automotive team of Capgemini.
The main objectives were to understand the usage experience, purchase drivers and touchpoints, triggers & barriers, and other factors influencing EV users and its intenders.
Both qualitative and quantitative approaches were used for the study with respondents categorized into three target groups – EV Owners, Intenders and Non-intenders.
15 IDI’s were conducted across the target groups and the insights generated were verified and analyzed through face-to-face CAPI interviews (N=400).
The study focused on all stage of an EV consumer journey from pre-purchase phase, purchase and decision-making process, and the post-purchase phase.
The demographics of respondents, their daily car usage patterns and perceptions about EV were also studied for better understanding and analysis.
A detailed report with graphical representations of the analysis, report and insights derived from the study was delivered to the automotive team.

## Slide 28: OUR MULTIDISCLINARY TEAMS enable us to leverage SMEs on key tenets of this project
frog Innovation, Strategy & Design
frog Brand & Content
frog Customer Transformation
frog Data & Analytics
Marketing
Customer Strategy & Performance
“Data, AI & Analytics Services” for Marketing
Design
Growth Strategy
Brand
Sales Transformation
Customer Platforms & Services
Digital Content
Commerce Transformation
Sales
Services Transformation
Smart Products & New Business Model
Intelligent & Sustainable Operations
Intelligent Industry Data & Analytics
Connected Products & Services
Supply Chain Transformation
“Data, AI & Analytics Services” for Intelligent Industry
Digital Eng. & R&D
Smart Plant
Innovative & Industrial Tech & Platforms
Industrial Procurement
Discrete Manufacturing
Process Manufacturing
Complex Infrastructures
Services Sectors
Corporate Experience
Workforce & Organization
Business Technology
Enterprise Data & Analytics
Workforce Transformation
Data Driven Finance Risk & Compliance
Enterprise Model and Strategy
Procurement Transformation
Program & Change Acceleration
Intelligent Process & Performance
Employee Experience & HR
Servitization
Cloud Transform
Technology Innovation
Digital Trust & Security
Digital Workplace
Digital IT Acceleration
IT Perform. & IT PMI
Data Strategy & Factory
Finance &
S/4 Transformation
Organization Purpose & Strategy
CoE in India: People Analytics
Primary Research
Strategic Research
DATA ACCELERATION
Training Capabilities
frog
CUSTOMER FIRST
INTELLIGENT
INDUSTRY
ENTERPRISE
TRANSFORMATION
INDIA CoE
PMI

## Slide 29
Our understanding of your needs
Our approach
Our assets to support you
Appendix
1
2
3
4
BlaBlaCar market research proposal | September 2023

## Slide 30
OUR APPROACH FOR USER RESEARCH
Study the societal, macroeconomic, regulatory, and carpooling trends most likely to shape the future - and the potential disruptive events that may change that course. Evaluate how BlaBla car may thrive within them.
Identify carpooling trends and disruptors
Leverage internal and external viewpoints
Develop durable perspectives
Combine insight with commercial reality
Capture internal perspective and predictions for the future of mobility, and reflections on past successes and failures. Supplement with external subject matter expertise, ensuring a holistic view of what may happen - and how to interpret what already has.
Working in partnership with BlaBla car, develop a shared understanding of what the future of mobility may hold, identifying the plausible impact on the mobility ecosystem and the likely opportunities that arise from it.
Prioritize future opportunities through a rigorous qualitative and quantitative approach, identifying areas where BlaBla car is most poised to succeed - and not just where potential lies dormant.
© confidential 2021 | frog Part of Capgemini Invent

## Slide 31
Our approach
Explore and identify the trends, potential disruptions, and likely futures of the mobility industry, through a bespoke primary and secondary research exercise. Generate 10-15 hypotheses, to be evaluated and discussed with the BlaBla car team.
Create questionnaire, identify users for research.
Expert/Stakeholder Interviews
Document Review
Key Activities
User research in user’s environment to understand attitudes towards car pooling, their needs, identify gaps in the product and brand perception.
Develop a “Gameboard” of 10-12 Opportunity Areas, defining the areas of carpooling most ripe for BlaBla car to expand in Indian market.
User interviews
Field research Synthesis
Develop and refine an understanding of the potential size of prize, profit pools, and capability gaps for each opportunity space, prioritizing opportunities for further study and investment through a holistic evaluation.
Survey
© confidential 2021 | frog Part of Capgemini Invent
Immerse — 03 weeks
Define — 04 weeks
Assess — 02 weeks

## Slide 32: Product fit proposed approach
Goals
Main activities
Methodology
Deliverables
Define BlaBlaCar’s carpooling and Pro Marketplace market fit in India
Assess target users’ usage and perception of BBC’s main products
  Awareness, usage and perceptions of carpooling/ bus booking apps
  First thoughts, spontaneous likes, spontaneous dislikes of the proposed concepts
  Ratings of the concepts: uniqueness, relevance, believability and comprehension of the concepts, ratings on specific product attributes
  Intention to try/ improvement areas
  Benchmark BBC’s products against market leaders’
  Missing features
  Delight areas
Gap analysis between BlaBlaCar carpooling platform and customer expectations
Gap analysis between Pro marketplace and customer expectations
Executive memo highlighting key findings
Desk research based on publicly available sources and phase 1 interviews
Face-to-face interviews in the local language with target users of carpooling and the Pro marketplace in India

## Slide 33: Product Fit detailed project plan
N. | Activities | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
2 | Product Fit |  |  |  |  |  | 
2.1 | Finalization of Survey Questionnaire |  |  |  |  |  | 
2.2 | Field Briefing and Set up |  |  |  |  |  | 
2.3 | Fieldwork – conducting face-to-face interviews |  |  |  |  |  | 
2.4 | Data cleaning/ validation and processing |  |  |  |  |  | 
2.5 | Survey insights and conclusions (extent of product fit/ gaps if any) |  |  |  |  |  | 
2.6 | Create Market overview draft in PPT & summarize key learnings in Word |  |  |  |  |  | 
Workshop to discuss progress
Kick off
Final presentation deliverables to BlaBlaCar stakeholders
Notes: High level benchmark
Gap analysis in primary reasearch

## Slide 34: Product Fit research methodology
Survey to be conducted among potential users
Objectives
Assess BlaBlaCar carpooling platform product fit with target users
Assess acceptance of carpooling
Understand main blockers to carpool if any
Assess BlaBlaCar pro marketplace platform product fit with target users
Assess acceptance of pro marketplace
Understand main blockers to pro marketplace if any
Understand outstation travel patterns (frequency, booking, technology usage, etc.)
Research Methodology
Face-to-face interviews would be used to collect the desired information from the potential users
A structured questionnaire would be used to obtain responses from a statistically significant sample
This technique is eminently suitable in gathering feedback that is objective/ decisive, based on robust sample sizes
Target User
Potential User of the test product
Males/ females
SEC A / SEC B ***
Age: 25 to 45 years
Staying in one of the locations: Hyderabad, Bengaluru, Mumbai, Delhi, Pune
Inter-city travel (> 50 kms from city )
5 to 6 hours of travel time and/ or overnight journey
Frequent/ Occasional travelers *
Sample Size
Caveats & Assumptions
Target audiences in terms of age group, SEC ***, location etc. and city coverage to be finalized in consultation with the client​
It is assumed that two concepts are to be evaluated through the primary survey viz. carpooling and pro market place
Finalized value propositions to be provided by the client both in terms of carpooling as well as ProMarketplace​ concepts
Formats for the value proposition/ concepts would be suggested by the CG research team. Content should include need state, benefit statement, support statement, payoff
Questionnaire to be designed by the CG research team and finalized in consultation with the client​
Center | Concept 1 ** | Concept 2 **
Hyderabad | 70 | 70
Bengaluru | 70 | 70
Mumbai | 70 | 70
Delhi | 70 | 70
Pune | 70 | 70
Total sample | 350 | 350
*Minimum Quota of frequent travelers of N=50 potential users
** Concept 1: Carpooling concept and Concept 2: ProMarketplace concept
*** SEC is socioeconomic class based on education & occupation of chief wage earner

## Slide 35: Commercial breakdown
Phase 1
# man days
Phase 2
Cost
Total cost
€46,875
€49 035
Project lead
Project manager
Industry SME
Research consultants
Vendor costs
Primary research
Research consultants
Secondary research
10
25
25
30
N/A
75
€5,565
€7,387
€8,775
€19,635
# man days
Cost
10
25
3
36
N/A
40
€5,565
€7,387
€26,856
€8,340
Pending approval by Invent FR

## Slide 36: WE BRING A PROVEN TRACK RECORD HELPING CLIENTS WORLDWIDE in the mobility sector (5/6)
CRITICAL ASSESSMENT OF THE PROPOSED CLOUD-BASED PRODUCT OFFERING AND OPTIMUM PRICING FOR A U.S. CLIENT’S GO-TO-MARKET STRATEGY
CONTEXT
SOLUTION
IMPACT
Evaluation on several key metrics indicating customer preference as well as market acceptance benchmarks
Overall Appeal, Relevance and Uniqueness of the concepts for Design and Operations Hubs
Most preferred pricing levers based on multiple dimensions including number of users, number of connections and usage consumption
Optimum Price Ranges and Likely Pricing Points
Opportunity Assessment Accelerator & Van Westendorp Pricing Model used which provided comprehensive assessment of the market and actionable feedback for client’s go-to-market strategy prior to launch of new product offering
Objective evaluation of each of the concepts on proposed features/ benefits to be focused upon
Acceptable pricing options to the customer considering the price-quality equation
Evaluation among client’s own customers as well as those using competitive offerings
Devising marketing elements of the client’s go-to-market strategy including product features as well as service differentiators offering a competitive edge and subscription plans for appropriate pricing of the product offering

## Slide 37: Deliverables of the Project
MARKET ANALYSIS
Mobility Market Landscape Mobility market landscape in 7 identified cities (primarily Tier 1 cities) including market size/growth, trends, ease of availability, political and economic ecosystem etc. with a deep dive in bus industry along with a view of main routes
Mobility marketplace solution General assessment of various tech layers of mobility marketplace solution, with a view on relevant players on each layer
Relevant market players Deep dive on relevant market players (bus operators/travel agents) in target regions providing insights on market structure & commercials
PRODUCT FIT
Final assessment An executive synthesis for final presentation with stakeholders will be drafted at the end of the project to track and enclose all the key information and decisions made throughout the project
Usage and Perceptions Awareness, usage and perceptions of carpooling/ bus booking apps
Spontaneous Reactions First thoughts, spontaneous likes, spontaneous dislikes of the proposed concepts
Ratings of the concepts Metrics like appeal, uniqueness, relevance, believability and comprehension of the concepts. Overall ratings and ratings on specific product attributes relevant to the category/ brand, comparison versus current product
Intention to try/ improvement areas The likelihood of trial and reasons thereof, suggestions for improvement

## Slide 38: We Have Access to a Range of Premium Databases to Provide Strategic Data
REPRESENTATIVE SETS
INTERNAL INTELLIGENCE
SMEs from Automotive domain and technological aspects of a digital solution with deep expertise in Indian market
INTERVIEWS & SURVEYS
PUBLICLY PUBLISHED
STUDIES
IN-HOUSE
INTERVIEWS & SURVEYS
with a network of experts as well as a panel of new / existing consumers through phone calls/ online techniques to gain powerful insights
PUBLIC SOURCES
Publicly available information related to regional stats, economy, key trends etc.
Capgemini accelerators work in background to analysis and synthetase in very short time.
BLABLACAR INTERVIEWS
BlaBlaCar Stakeholder interviews
In-house SME insights
Insights from
Capgemini reports
In-house Panel Procurement Team for vendor selection, administrative support and coordination
Offering local language support for interviews/ moderation, questionnaire/ discussion guide translations
Strong data expertise to provide multi-mode sampling, de-duplication, and data checks to ensure data quality
Pool of hard-to-reach, high-quality, online & offline, B2B, B2C, ITDM, and healthcare census samples
Access to over 70 million panelists across 80+ countries from our 150 certified global sample partners
PANEL - GLOBAL OUTREACH

## Slide 39: WE BRING A PROVEN TRACK RECORD HELPING CLIENTS WORLDWIDE in the mobility sector (3/3)
MAXI
CONTEXT
SOLUTION
IMPACT
Lorem ipsum dolor sit amet, consetetur sadipscing elitr, sed diam nonumy eirmod tempor invidunt ut labore et dolore magna aliquyam erat, sed diam voluptua.
Lorem ipsum dolor sit amet, consetetur sadipscing elitr, sed diam nonumy eirmod tempor invidunt ut labore et dolore magna aliquyam erat, sed diam voluptua.
Lorem ipsum dolor sit amet, consetetur sadipscing elitr, sed diam nonumy eirmod tempor invidunt ut labore et dolore magna aliquyam erat, sed diam voluptua.
Update with Maxi credential

## Slide 40: Our understanding
BlaBlaCar had entered Indra in 2015 and launched it’s poolcar platform
BlaBlaCar now plans to expand business in India
BlaBlaCar wants to explore alternative landscape (personal car/ bus/ train/ plane) in India
Explore Business opportunity in bus industry for intercity commute
Design offerings for customers and partners
Background & Objective1
Source:
1. https://yourstory.com/2023/04/blablacar-expands-india-new-delhi-office; 2. https://auto.economictimes.indiatimes.com/news/blablacar-looking-to-expand-business-in-india-plans-to-set-up-first-office-in-ncr/99442783#:~:text=BlaBlaCar%20allows%20the%20drivers%20to,It's%20carpooling%20and%20Intercity%20carpooling.%22&text=The%20company%2C%20which%20launched%20its,an%20office%20in%20the%20country.
BlaBlaCar planning to expand operations in India2
BlaBlaCar acquires 4 Mn users rapidly in India1
News
Notes: BlaBlaCar started operations in India in 2015, targeting medium-range trips and a young demography, with relative success compared to investments

## Slide 41: Factors driving transition from ownership to usership in india
Source:
1.Report from NITI Aayog “MOVE GLOBAL MOBILITY SUMMIT, Sep. 7 & 8, 2018 “. “Moving Forward Together – Enabling Shared Mobility in India”;2. https://www.statista.com/statistics/467163/forecast-of-smartphone-users-in-india/; 3. https://www.statista.com/statistics/255146/number-of-internet-users-in-india/; 3. https://www.statista.com/statistics/255146/number-of-internet-users-in-india/; 4. https://www.globaldata.com/data-insights/macroeconomic/urbanization-rate-in-india-2096096/#:~:text=2022%20Source%3A%20GlobalData-,Urbanization%20Rate%20in%20India,the%20indicator%20increased%20by%2019.6%25.; 5. https://www.statista.com/outlook/co/macroeconomic-indicators/disposable-income/india#household-disposable-income; 6. https://pib.gov.in/PressReleasePage.aspx?PRID=1888480; * https://www.financialexpress.com/business/roadways-highway-construction-target-raised-to-13800-km-for-fy23-3180341/; 7. https://www.frost.com/news/press-releases/indias-increasing-demand-for-transportation-services-expedites-shared-mobility-market-growth/;
India is expected to be a leader in shared mobility with shared miles expected to reach 35% of all the miles travelled by 2030 and 50% by 20401
Low per capita vehicle ownership and a high share of public transit (~3% of population possess personal vehicles)1
Factors driving ride sharing in India1
Supportive framework for shared mobility -supportive policies for shared mobility and digitization to regulate the shared mobility ecosystem
Young population and growing entrepreneurial culture - More than 50% of the population in India is below the age of 25 and more than 65% is below the age of 35.
Growing smartphone penetration and internet connectivity - Smartphone penetration in India is expected to grow to 1 billion in 20232 active users while the number of internet users is expected to reach 1.2 billion by 20233
Indian national highways has been increasing @ ~15% over FY15-236
Chart: 
| FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23*
National Highways (Length in '000 K.M.) | 4.4 | 6.1 | 8.2 | 9.8 | 10.8 | 10.2 | 13.3 | 10.4 | 13.8
15.4%
CAGR
Development of Roads and Infrastructure will promote shared mobility in different formats (Poolcar / Bus etc.) for intercity travel
Growing urbanization(growth rate of 19.6%)4 and rising disposable income (CAGR FY18 to FY23 8.2%)5 signal growth opportunities in the Indian shared mobility market7
Notes: Demography: Young population with growing disposable income and smartphone adoption
Sustainability: Sustainability concerns make local governments promote alternatives
Infrastructure: Infrastructure improvements
Lack of affordable travel options for last-minute trips: trains booked early, low per capita vehicle ownership

## Slide 42: Factors driving transition from ownership to usership in india
Source:
1.Report from NITI Aayog “MOVE GLOBAL MOBILITY SUMMIT, Sep. 7 & 8, 2018 “. “Moving Forward Together – Enabling Shared Mobility in India”;2. https://www.statista.com/statistics/467163/forecast-of-smartphone-users-in-india/; 3. https://www.statista.com/statistics/255146/number-of-internet-users-in-india/;
India is expected to be a leader in shared mobility with shared miles expected to reach 35% of all the miles travelled by 2030 and 50% by 20401
Low per capita vehicle ownership and a high share of public transit
Factors driving ride sharing in India1
Supportive framework for shared mobility -supportive policies for shared mobility and digitization to regulate the shared mobility ecosystem
Young population and growing entrepreneurial culture - More than 50% of the population in India is below the age of 25 and more than 65% is below the age of 35.
Growing smartphone penetration and internet connectivity - Smartphone penetration in India is expected to grow to 1 billion in 20232 active users while the number of internet users is expected to reach 1.2 billion by 20233
Indian national highways has been increasing @ ~7.5% over FY11-20
Chart: 
| FY11 | FY17 | FY20 | FY22E | FY25P
National Highways (Length in '000 K.M.) | 71 | 104 | 136 | 141 | 200